## Combination
Walmart AI transformation adpotion ERM
ERM logic flow | Q1 | Why is Walmart doing AI Transformation?
Walmart is facing challenges from Aamzon and other retailers. To improve operational efficiency, reduce costs, optimize supply chain management and enhance customer experience.
| Q2 | What actually Walmart do?
Walmart partered with Symbotic, an AI-powered robitics and warehouse automation company, to automate its distribution centers and fulfillment operations. The adoption and tranforamtion including: AI warehouse robotics, automated inventory management, smart fulfillment system, AI logistics optimization, predictive supply chain analytics and atuomated picking and sorting system. At the same time, Walmart aslo invested in atuomated fulliment centers and smart retail infrastructure.
Internal Control | Buiness Process | Impacted Buiness Processes after Walmart AI tranformation
|  | Procurement Porcess | Inventory Management Process | Warehouse & Fulfillment Process | Supply Chain & Logistics Process | POS & Payment Process | Customer Data Analytics Process | Human Resource Process | Fixed Assets & Facilities Process | Information system Process
Explaination |  | Walmart is transforming from a traditional retail model with manual and decentralized operations into an AI-driven automated retail model that increasingly relies on centralized technology and cloud-based controls. These internal buiness process was impacted after transofrmation.
Walmart AI Transformation — ERM Risk Register & Risk Control Matrix
Buinesee Process |  | Top-level Risk (ERM Category) | Secondary Risk | Risk Description |  | KRIs | Contributing Factors |  | Controls |  | Risk Owner
Procurement Process |  | Operational Risk | AI forecasting error risk | AI forecasting systems may generate inaccurate purchasing recommendations, resulting in over-purchasing, under-purchasing, stock shortages, and inventory imbalance. |  | Forecast Accuracy %, Stockout Frequency, Procurement Variance % | Poor data quality, AI model bias, unstable customer demand |  | AI model validation, management review, procurement approval workflow |  | Procurement Department
|  | Operational Risk | Unauthroized Procurement Risk | Automated procurement systems may bypass management approval and authorization controls |  | Unauthorized Purchase Incidents, Approval Exception Rate | Weak approval workflow, insufficient segregation of duties |  | Multi-level approval controls, segregation of duties |  | Procurement & Compliance Team
|  | Third-Party Risk | Supplier Concentration Risk | Overdependence on a limited number of suppliers may increase supply chain disruption risk. |  | Supplier Concentration Ratio, Supplier Failure Incidents | Limited supplier diversification, cost-driven sourcing |  | Supplier diversification, supplier due diligence |  | Supplier Management Team
|  | Compliance Risk | Precurement Compliance Violation risk | Procurement activities may violate internal procurement policies or ESG requirements. |  | Procurement Compliance Violations, Audit Findings | Weak compliance governance, inadequate compliance review |  | Compliance review procedures, procurement policy enforcement |  | Procurement & Compliance Team
|  | Financial&Operational Risk | Over-purchasing Risk | Excessive purchasing caused by inaccurate AI demand forecasting may increase inventory carrying costs. |  | Inventory Carrying Cost, Overstock Ratio | Forecast inaccuracies, weak demand planning |  | Demand planning review, forecasting adjustment procedures |  | Procurement & Finance Team
|  | Operational Risk | Under-purchaseing Risk | Insufficient purchasing may result in stock shortages and customer dissatisfaction. |  | Stockout Frequency, Fulfillment Delay % | Demand volatility, inaccurate forecasting |  | Safety stock management, procurement monitoring dashboard |  | Procurement Department
|  | Compliance&Operational Risk | Procurement Approval Failure Risk | Procurement approval controls may fail due to excessive automation and weak oversight. |  | Approval Exception Rate, Unauthorized Procurement Cases | Overreliance on automation, weak internal controls |  | Approval hierarchy controls, exception reporting |  | Procurement Department
|  | Operational Risk | Goods receiving verification failure risk | Warehouse receiving systems may incorrectly verify incoming goods. |  | Receiving Error Rate, Damaged Goods Acceptance Rate | Weak receiving inspection |  | Physical inspection procedures, barcode verification |  | Warehouse Operations Team
|  | Technology&Operational Risk | Warehouse Entry synchronization Failure Risk | Inventory data may fail to synchronize correctly during warehouse entry. |  | Inventory Reconciliation Difference | Weak system integration, cloud synchronization issues |  | Real-time synchronization monitoring, backup systems |  | IT Infrastructure Team
|  | Financial&Compliance Risk | Procurement Fraud Risk | Employees or suppliers may manipulate procurement transactions for fraudulent activities. |  | Fraud Incident Frequency, Procurement Audit Findings | Weak monitoring, insufficient segregation of duties |  | Fraud monitoring analytics, internal audit review |  | Internal Audit & Procurement Team
Inventory Mngt Process |  | Operational Risk | Inventory Mismatch Risk | Inventory records may not match physical inventory due to AI errors. |  | Inventory Accuracy %, Inventory Reconciliation Difference % | weak reconciliation |  | Inventory reconciliation, cycle counting |  | Inventory Control Team
|  | Operational Risk | Inventory Reconciliation Failure Risk | Inventory reconciliation procedures may fail to identify discrepancies. |  | Inventory Reconciliation Difference %, Shrinkage % | Weak reconciliation procedures, poor monitoring |  | Automated reconciliation alerts, management review |  | Inventory Audit Team
|  | Buiness Continutiy Risk | Warehouse Operational Disruption Risk | Inventory system failures may disrupt warehouse operations. |  | Warehouse Downtime, Fulfillment Delay % | System outages, infrastructure dependency |  | Disaster recovery planning, backup warehouse systems |  | Warehouse Operations Team
|  | Financial&Operational Risk | Inventory Shrinkage Risk | Inventory theft or inaccurate tracking may increase inventory shrinkage. |  | Inventory Shrinkage % | Weak inventory controls, limited monitoring |  | CCTV monitoring, inventory audits |  | Inventory Security Team
|  | Technology Risk | Real-time Inventory Tracking Failure Risk | AI systems may fail to track inventory movements in real time. |  | Inventory Visibility %, Real-Time Tracking Failure Rate | Cloud synchronization delays, system integration issues |  | Real-time system monitoring, backup tracking procedures |  | IT & Inventory Operations Team
Warehouse & Fulfillment Process |  | Technology Risk | Robotics System Failure Risk | Warehouse robotics systems may malfunction and interrupt automated warehouse operations. |  | Robotics Failure Frequency, Warehouse Downtime | Poor maintenance, system overload, software malfunction |  | Preventive maintenance, backup operational procedures |  | Warehouse Operations Team
|  | Technology&Operational Risk | Automated Sorting Failure Risk | Automated sorting systems may incorrectly classify or route products during fulfillment operations. |  | Sorting Error Rate, Fulfillment Accuracy | Sensor failure, weak calibration, AI model inaccuracies |  | Sensor testing, quality control review |  | Fulfillment Operations Team
|  | Buiness Continutiy Risk | Warehouse Downtime Risk | Warehouse systems may become unavailable due to infrastructure outages or system failures. |  | Warehouse Downtime, Recovery Time | Infrastructure dependency, cloud outages |  | Disaster recovery planning, infrastructure redundancy |  | Warehouse & IT Infrastructure Team
|  | Operational Risk | Fulfillment Delay Risk | Automated fulfillment processes may fail to process orders efficiently during peak demand periods. |  | Fulfillment Delay %, Order Backlog Volume | Operational bottlenecks, robotics issues |  | Fulfillment monitoring dashboard, escalation procedures |  | Fulfillment Management Team
|  | Technology Risk | Smart Fulfillment System Failure Risk | Smart fulfillment systems may fail due to cloud synchronization issues or high transaction volumes. |  | System Availability %, Fulfillment Failure Rate | Cloud synchronization failure, weak scalability |  | Load balancing, system scalability planning |  | IT Operations Team
|  | Facilities Risk | Warehouse Capacity Constraint Risk | Warehouse capacity limitations may reduce storage efficiency and delay order processing. |  | Warehouse Capacity Utilization %, Order Delay Frequency | Poor space planning, seasonal demand spikes |  | Warehouse optimization planning, overflow contingency |  | Facilities Management Team
|  | Operational&Facilites Risk | Warehouse Safety Incident Risk | Automated warehouse operations may increase employee safety risks involving robotics equipment and automated machinery. |  | Safety Incident Frequency, Lost Time Injury Rate | Weak safety procedures, insufficient employee training |  | Safety training, equipment safety inspections |  | Safety Team
Supply Chain & Logistics Process |  | Operational Risk | Supply Chain Disruption Risk | AI logistics failures may disrupt supply chain operations and product deliveries. |  | Delivery Delay %, Logistics Interruption Frequency | Transportation dependency, AI routing errors |  | Logistics contingency planning, route verification |  | Logistics Department
|  | Technology Risk | AI Routing Error Risk | AI routing systems may generate inefficient or incorrect delivery routes. |  | Route Optimization Accuracy %, Delivery Delay % | Poor traffic data, AI model inaccuracies |  | Route monitoring, AI model recalibration |  | Logistics Department
|  | Buiness Continutiy Risk | Distribution Center Failure Risk | Distribution center outages may interrupt regional supply chain operations |  | Distribution Center Downtime, Recovery Time | Infrastructure dependency, centralized operations |  | Backup distribution centers, failover systems |  | Distribution Center Operations Team
|  | Operational Risk | Transportation Delay Risk | Transportation disruptions may delay deliveries and increase logistics inefficiency |  | Transportation Incident Frequency, Delivery Delay % | Weather conditions, third-party carrier issues |  | Transportation monitoring, alternative carrier arrangements |  | Transportation Management Team
|  | Technology Risk | Logistics System Outage Risk | Logistics management systems may become unavailable during operations due to infrastructure or cloud failures |  | System Downtime, Recovery Time | Weak infrastructure, cloud dependency |  | Backup logistics systems, disaster recovery |  | IT Logistics Support Team IT
|  | Third-Party Risk | Third-Party Logistics Failure Risk | Third-party logistics providers may fail to meet operational or delivery requirements |  | SLA Violations, Vendor Incident Frequency | Vendor dependency, weak vendor oversight |  | Vendor performance review, SLA monitoring |  | Vendor Management Team
|  | Financial Risk | Fuel Cost Volatility Risk | Transportation fuel cost fluctuations may significantly increase logistics operating expenses |  | Fuel Cost Variance %, Logistics Cost Increase % | Market fuel price fluctuations, inefficient routing |  | Fuel hedging strategy, route optimization |  | Logistics Finance Team
|  | Technology&Operational Risk | Supply Chain Visibility Failure Risk | AI systems may fail to provide accurate real-time supply chain visibility across logistics operations |  | Supply Chain Visibility %, Real-Time Tracking Accuracy | Weak system integration, delayed data synchronization |  | Real-time monitoring dashboards, integrated logistics systems |  | Supply Chain Analytics Team
POS & Payment Process |  | Cybersecurity Risk | Payment Data Breach Risk | Cyber attackers may gain unauthorized access to customer payment information through POS systems or cloud-connected payment infrastructure |  | Cybersecurity Incidents, Unauthorized Access Attempts | Weak cybersecurity controls, cloud dependency |  | MFA, end-to-end encryption, cybersecurity monitoring |  | IT Security Team
|  | Operational Risk | POS System Outage Risk | POS systems may become unavailable due to infrastructure outages, software failure, or cloud synchronization issues |  | POS Downtime, System Recovery Time POS | Weak infrastructure, centralized system dependency |  | Backup POS systems, disaster recovery procedures |  | Retail Operations Team
|  | Fraud Risk | Fraudulent Transaction Risk | Fraudulent transactions may increase due to weaknesses in self-checkout systems and AI fraud detection models |  | Fraud Transaction Rate, Shrinkage % | Weak fraud monitoring, insufficient employee oversight |  | Fraud analytics monitoring, transaction review |  | Fraud Monitoring Team
|  | Information Security Risk | Unauthorized Access Risk | Unauthorized users may gain access to payment systems or customer transaction data due to weak access controls |  | Unauthorized Access Attempts, Security Alerts | Weak password controls, insufficient authentication |  | Role-based access control, MFA, access logging |  | IT Infrastructure Team
|  | Fraud Risk | Self-Checkout Fraud Risk | Customers may intentionally bypass product scanning or manipulate self-checkout systems |  | Self-Checkout Shrinkage %, Fraud Incident Frequency | Reduced employee supervision, weak monitoring |  | AI fraud detection, CCTV monitoring, transaction review |  | Retail Store Operations Team
|  | Technology&Operational Risk | Transaction Processing Failure Risk | Payment transactions may fail due to network interruptions or cloud payment system outages |  | Payment Failure Rate, Transaction Recovery Time | Network instability, cloud synchronization failure |  | Backup payment processing systems, network redundancy |  | Payment Operations Team
Customer Data Analytics Process |  | Compliance Risk | Customer Privacy Violation Risk | AI analytics systems may improperly collect, store, or process customer personal information |  | Privacy Complaints, Regulatory Audit Findings | Weak privacy governance, excessive data collection |  | Privacy compliance audit, data minimization policy |  | Data Governance Team
|  | Information Security Risk | Customer Data Breach Risk | Customer data stored in AI systems or cloud databases may be exposed through cyberattacks |  | Data Breach Incidents, Security Incident Frequency | Weak cybersecurity controls, cloud dependency |  | Encryption, cybersecurity monitoring, access restrictions |  | IT Security Team
|  | Reputational Risk | Regulatory Non-Compliance Risk | AI customer analytics activities may violate data privacy laws such as GDPR or CCPA |  | Compliance Violations, Regulatory Findings | Weak regulatory monitoring, poor compliance governance |  | Compliance review procedures, legal oversight |  | Compliance Department
|  | Reputational Risk | Customer Trust Risk | Customers may lose trust in Walmart if AI systems misuse customer data or generate unfair recommendations |  | ustomer Trust Score, Customer Complaint Frequency | Poor transparency, weak customer communication |  | Customer transparency policy, AI governance communication |  | Customer Experience Team
Human Resource Process |  | Human Capital Risk | Employee Resistance Risk | Employees may resist AI transformation due to concerns regarding job displacement and operational changes |  | Employee Satisfaction Score, Employee Turnover Rate | Fear of automation, poor communication |  | Change management programs, employee communication strategy |  | HR Department
|  | Operational Risk | Skill Gap Risk | Employees may lack technical skills required to operate AI-enabled systems effectively |  | Training Completion %, AI Adoption Rate | Insufficient AI training, rapid technology implementation |  | AI training programs, operational support |  | HR Department
|  | Human Capital Risk | Employee Turnover Risk | Employees with critical operational or technical knowledge may leave during AI transformation |  | Employee Turnover Rate, Retention Rate | Organizational uncertainty, low morale |  | Talent retention plans, employee engagement strategy |  | HR Department
|  | Operational Risk | Operational Error Risk | Employees may incorrectly operate AI-enabled systems during transition periods |  | Operational Error Frequency, Incident Reports | Lack of operational training, weak supervision |  | Standard operating procedures, operational review |  | Operations Management Team

## ERM Risk Register & Risk Contro
Walmart AI Transformation — ERM Risk Register & Risk Control Matrix
Buinesee Process | Top-level Risk (ERM Category) | Secondary Risk | Risk Description | KRIs | Contributing Factors | Controls | Risk Owner
Procurement Process | Operational Risk | AI forecasting error risk | AI forecasting systems may generate inaccurate purchasing recommendations, resulting in over-purchasing, under-purchasing, stock shortages, and inventory imbalance. | Forecast Accuracy %, Stockout Frequency, Procurement Variance % | Poor data quality, AI model bias, unstable customer demand | AI model validation, management review, procurement approval workflow | Procurement Department
Procurement Process | Operational Risk | Unauthroized Procurement Risk | Automated procurement systems may bypass management approval and authorization controls | Unauthorized Purchase Incidents, Approval Exception Rate | Weak approval workflow, insufficient segregation of duties | Multi-level approval controls, segregation of duties | Procurement & Compliance Team
Procurement Process | Third-Party Risk | Supplier Concentration Risk | Overdependence on a limited number of suppliers may increase supply chain disruption risk. | Supplier Concentration Ratio, Supplier Failure Incidents | Limited supplier diversification, cost-driven sourcing | Supplier diversification, supplier due diligence | Supplier Management Team
Procurement Process | Compliance Risk | Precurement Compliance Violation risk | Procurement activities may violate internal procurement policies or ESG requirements. | Procurement Compliance Violations, Audit Findings | Weak compliance governance, inadequate compliance review | Compliance review procedures, procurement policy enforcement | Procurement & Compliance Team
Procurement Process | Financial&Operational Risk | Over-purchasing Risk | Excessive purchasing caused by inaccurate AI demand forecasting may increase inventory carrying costs. | Inventory Carrying Cost, Overstock Ratio | Forecast inaccuracies, weak demand planning | Demand planning review, forecasting adjustment procedures | Procurement & Finance Team
Procurement Process | Operational Risk | Under-purchaseing Risk | Insufficient purchasing may result in stock shortages and customer dissatisfaction. | Stockout Frequency, Fulfillment Delay % | Demand volatility, inaccurate forecasting | Safety stock management, procurement monitoring dashboard | Procurement Department
Procurement Process | Compliance&Operational Risk | Procurement Approval Failure Risk | Procurement approval controls may fail due to excessive automation and weak oversight. | Approval Exception Rate, Unauthorized Procurement Cases | Overreliance on automation, weak internal controls | Approval hierarchy controls, exception reporting | Procurement Department
Procurement Process | Operational Risk | Goods receiving verification failure risk | Warehouse receiving systems may incorrectly verify incoming goods. | Receiving Error Rate, Damaged Goods Acceptance Rate | Weak receiving inspection | Physical inspection procedures, barcode verification | Warehouse Operations Team
Procurement Process | Technology&Operational Risk | Warehouse Entry synchronization Failure Risk | Inventory data may fail to synchronize correctly during warehouse entry. | Inventory Reconciliation Difference | Weak system integration, cloud synchronization issues | Real-time synchronization monitoring, backup systems | IT Infrastructure Team
Procurement Process | Financial&Compliance Risk | Procurement Fraud Risk | Employees or suppliers may manipulate procurement transactions for fraudulent activities. | Fraud Incident Frequency, Procurement Audit Findings | Weak monitoring, insufficient segregation of duties | Fraud monitoring analytics, internal audit review | Internal Audit & Procurement Team
Inventory Mngt Process | Operational Risk | Inventory Mismatch Risk | Inventory records may not match physical inventory due to AI errors. | Inventory Accuracy %, Inventory Reconciliation Difference % | weak reconciliation | Inventory reconciliation, cycle counting | Inventory Control Team
Inventory Mngt Process | Operational Risk | Inventory Reconciliation Failure Risk | Inventory reconciliation procedures may fail to identify discrepancies. | Inventory Reconciliation Difference %, Shrinkage % | Weak reconciliation procedures, poor monitoring | Automated reconciliation alerts, management review | Inventory Audit Team
Inventory Mngt Process | Buiness Continutiy Risk | Warehouse Operational Disruption Risk | Inventory system failures may disrupt warehouse operations. | Warehouse Downtime, Fulfillment Delay % | System outages, infrastructure dependency | Disaster recovery planning, backup warehouse systems | Warehouse Operations Team
Inventory Mngt Process | Financial&Operational Risk | Inventory Shrinkage Risk | Inventory theft or inaccurate tracking may increase inventory shrinkage. | Inventory Shrinkage % | Weak inventory controls, limited monitoring | CCTV monitoring, inventory audits | Inventory Security Team
Inventory Mngt Process | Technology Risk | Real-time Inventory Tracking Failure Risk | AI systems may fail to track inventory movements in real time. | Inventory Visibility %, Real-Time Tracking Failure Rate | Cloud synchronization delays, system integration issues | Real-time system monitoring, backup tracking procedures | IT & Inventory Operations Team
Warehouse & Fulfillment Process | Technology Risk | Robotics System Failure Risk | Warehouse robotics systems may malfunction and interrupt automated warehouse operations. | Robotics Failure Frequency, Warehouse Downtime | Poor maintenance, system overload, software malfunction | Preventive maintenance, backup operational procedures | Warehouse Operations Team
Warehouse & Fulfillment Process | Technology&Operational Risk | Automated Sorting Failure Risk | Automated sorting systems may incorrectly classify or route products during fulfillment operations. | Sorting Error Rate, Fulfillment Accuracy | Sensor failure, weak calibration, AI model inaccuracies | Sensor testing, quality control review | Fulfillment Operations Team
Warehouse & Fulfillment Process | Buiness Continutiy Risk | Warehouse Downtime Risk | Warehouse systems may become unavailable due to infrastructure outages or system failures. | Warehouse Downtime, Recovery Time | Infrastructure dependency, cloud outages | Disaster recovery planning, infrastructure redundancy | Warehouse & IT Infrastructure Team
Warehouse & Fulfillment Process | Operational Risk | Fulfillment Delay Risk | Automated fulfillment processes may fail to process orders efficiently during peak demand periods. | Fulfillment Delay %, Order Backlog Volume | Operational bottlenecks, robotics issues | Fulfillment monitoring dashboard, escalation procedures | Fulfillment Management Team
Warehouse & Fulfillment Process | Technology Risk | Smart Fulfillment System Failure Risk | Smart fulfillment systems may fail due to cloud synchronization issues or high transaction volumes. | System Availability %, Fulfillment Failure Rate | Cloud synchronization failure, weak scalability | Load balancing, system scalability planning | IT Operations Team
Warehouse & Fulfillment Process | Facilities Risk | Warehouse Capacity Constraint Risk | Warehouse capacity limitations may reduce storage efficiency and delay order processing. | Warehouse Capacity Utilization %, Order Delay Frequency | Poor space planning, seasonal demand spikes | Warehouse optimization planning, overflow contingency | Facilities Management Team
Warehouse & Fulfillment Process | Operational&Facilites Risk | Warehouse Safety Incident Risk | Automated warehouse operations may increase employee safety risks involving robotics equipment and automated machinery. | Safety Incident Frequency, Lost Time Injury Rate | Weak safety procedures, insufficient employee training | Safety training, equipment safety inspections | Safety Team
Supply Chain & Logistics Process | Operational Risk | Supply Chain Disruption Risk | AI logistics failures may disrupt supply chain operations and product deliveries. | Delivery Delay %, Logistics Interruption Frequency | Transportation dependency, AI routing errors | Logistics contingency planning, route verification | Logistics Department
Supply Chain & Logistics Process | Technology Risk | AI Routing Error Risk | AI routing systems may generate inefficient or incorrect delivery routes. | Route Optimization Accuracy %, Delivery Delay % | Poor traffic data, AI model inaccuracies | Route monitoring, AI model recalibration | Logistics Department
Supply Chain & Logistics Process | Buiness Continutiy Risk | Distribution Center Failure Risk | Distribution center outages may interrupt regional supply chain operations | Distribution Center Downtime, Recovery Time | Infrastructure dependency, centralized operations | Backup distribution centers, failover systems | Distribution Center Operations Team
Supply Chain & Logistics Process | Operational Risk | Transportation Delay Risk | Transportation disruptions may delay deliveries and increase logistics inefficiency | Transportation Incident Frequency, Delivery Delay % | Weather conditions, third-party carrier issues | Transportation monitoring, alternative carrier arrangements | Transportation Management Team
Supply Chain & Logistics Process | Technology Risk | Logistics System Outage Risk | Logistics management systems may become unavailable during operations due to infrastructure or cloud failures | System Downtime, Recovery Time | Weak infrastructure, cloud dependency | Backup logistics systems, disaster recovery | IT Logistics Support Team IT
Supply Chain & Logistics Process | Third-Party Risk | Third-Party Logistics Failure Risk | Third-party logistics providers may fail to meet operational or delivery requirements | SLA Violations, Vendor Incident Frequency | Vendor dependency, weak vendor oversight | Vendor performance review, SLA monitoring | Vendor Management Team
Supply Chain & Logistics Process | Financial Risk | Fuel Cost Volatility Risk | Transportation fuel cost fluctuations may significantly increase logistics operating expenses | Fuel Cost Variance %, Logistics Cost Increase % | Market fuel price fluctuations, inefficient routing | Fuel hedging strategy, route optimization | Logistics Finance Team
Supply Chain & Logistics Process | Technology&Operational Risk | Supply Chain Visibility Failure Risk | AI systems may fail to provide accurate real-time supply chain visibility across logistics operations | Supply Chain Visibility %, Real-Time Tracking Accuracy | Weak system integration, delayed data synchronization | Real-time monitoring dashboards, integrated logistics systems | Supply Chain Analytics Team
POS & Payment Process | Cybersecurity Risk | Payment Data Breach Risk | Cyber attackers may gain unauthorized access to customer payment information through POS systems or cloud-connected payment infrastructure | Cybersecurity Incidents, Unauthorized Access Attempts | Weak cybersecurity controls, cloud dependency | MFA, end-to-end encryption, cybersecurity monitoring | IT Security Team
POS & Payment Process | Operational Risk | POS System Outage Risk | POS systems may become unavailable due to infrastructure outages, software failure, or cloud synchronization issues | POS Downtime, System Recovery Time POS | Weak infrastructure, centralized system dependency | Backup POS systems, disaster recovery procedures | Retail Operations Team
POS & Payment Process | Fraud Risk | Fraudulent Transaction Risk | Fraudulent transactions may increase due to weaknesses in self-checkout systems and AI fraud detection models | Fraud Transaction Rate, Shrinkage % | Weak fraud monitoring, insufficient employee oversight | Fraud analytics monitoring, transaction review | Fraud Monitoring Team
POS & Payment Process | Information Security Risk | Unauthorized Access Risk | Unauthorized users may gain access to payment systems or customer transaction data due to weak access controls | Unauthorized Access Attempts, Security Alerts | Weak password controls, insufficient authentication | Role-based access control, MFA, access logging | IT Infrastructure Team
POS & Payment Process | Fraud Risk | Self-Checkout Fraud Risk | Customers may intentionally bypass product scanning or manipulate self-checkout systems | Self-Checkout Shrinkage %, Fraud Incident Frequency | Reduced employee supervision, weak monitoring | AI fraud detection, CCTV monitoring, transaction review | Retail Store Operations Team
POS & Payment Process | Technology&Operational Risk | Transaction Processing Failure Risk | Payment transactions may fail due to network interruptions or cloud payment system outages | Payment Failure Rate, Transaction Recovery Time | Network instability, cloud synchronization failure | Backup payment processing systems, network redundancy | Payment Operations Team
Customer Data Analytics Process | Compliance Risk | Customer Privacy Violation Risk | AI analytics systems may improperly collect, store, or process customer personal information | Privacy Complaints, Regulatory Audit Findings | Weak privacy governance, excessive data collection | Privacy compliance audit, data minimization policy | Data Governance Team
Customer Data Analytics Process | Information Security Risk | Customer Data Breach Risk | Customer data stored in AI systems or cloud databases may be exposed through cyberattacks | Data Breach Incidents, Security Incident Frequency | Weak cybersecurity controls, cloud dependency | Encryption, cybersecurity monitoring, access restrictions | IT Security Team
Customer Data Analytics Process | Reputational Risk | Regulatory Non-Compliance Risk | AI customer analytics activities may violate data privacy laws such as GDPR or CCPA | Compliance Violations, Regulatory Findings | Weak regulatory monitoring, poor compliance governance | Compliance review procedures, legal oversight | Compliance Department
Customer Data Analytics Process | Reputational Risk | Customer Trust Risk | Customers may lose trust in Walmart if AI systems misuse customer data or generate unfair recommendations | ustomer Trust Score, Customer Complaint Frequency | Poor transparency, weak customer communication | Customer transparency policy, AI governance communication | Customer Experience Team
Human Resource Process | Human Capital Risk | Employee Resistance Risk | Employees may resist AI transformation due to concerns regarding job displacement and operational changes | Employee Satisfaction Score, Employee Turnover Rate | Fear of automation, poor communication | Change management programs, employee communication strategy | HR Department
Human Resource Process | Operational Risk | Skill Gap Risk | Employees may lack technical skills required to operate AI-enabled systems effectively | Training Completion %, AI Adoption Rate | Insufficient AI training, rapid technology implementation | AI training programs, operational support | HR Department
Human Resource Process | Human Capital Risk | Employee Turnover Risk | Employees with critical operational or technical knowledge may leave during AI transformation | Employee Turnover Rate, Retention Rate | Organizational uncertainty, low morale | Talent retention plans, employee engagement strategy | HR Department
Human Resource Process | Operational Risk | Operational Error Risk | Employees may incorrectly operate AI-enabled systems during transition periods | Operational Error Frequency, Incident Reports | Lack of operational training, weak supervision | Standard operating procedures, operational review | Operations Management Team