## Sheet1
Risk # | The Risk of/That | Likelihood Score | Impact Score | Risk Score | Priority | Risk Strategy | Risk Response Plans
R4 | ROI Realization Failure from AI Transformation Investment | 5 | 8 | 40 | H | Mitigation | 1. Track financial returns in real time against projected targets 2. Link AI initiatives to measurable business KPIs
R5 | Inventory Forecast Error, Stockout Risk and Fulfillment Disruption | 7 | 8 | 56 | H | Mitigation | 1. Establish forecast accuracy monitoring dashboard 2. Implement exception alerts for abnormal inventory levels 3. require human review for critical inventory decisions
R6 | Legacy System Integration Failure and Vendor Dependency | 7 | 6 | 42 | H | Mitigation + Transfer | 1. Conduct integration Test 2. Deploy AI system in phases 3. Apply another techonology vendor
R7 | Customer Data Breach and Information Security Risk | 5 | 8 | 40 | H | Mitigation | 1. Continusously monitor forecast accuracy 2. Implement human review of critical forecast 3. Retrain AI models regularly
R8 | System Downtime and AI Platform Unavailability | 5 | 8 | 40 | H | Mitigation | 1. Expand AI training and workforce enablment programs 2. Monitor labor productivity KPIs 3. Align workforce incentives with AI adoption goals